## Risk Assessment
Risk Assessment ​
Risk​ | Risk Type​ | Affects​ | Description​ | Risk​ | Strategy​ | Potential indicator​ | Probability ​ | Effect​
Technical issues with web scraping ​ | Technical ​ | Project ​ | Websites having different structure causes issues with scarping text and can become a longer task. The websites can have limited access too which doesn’t allow web scraping.​ | The web scraping takes longer amount of time due to restrictions or a specific website is not allowing for web scraping at all. ​ | Research websites that may not allow web scraping to avoid getting banned. If unable to identify a div or anything that can allow for scraping text, move on to a different website. ​ | It is taking a long time to try to find something that could give access to the text. The code errors and is not proving any web scraping.​ | High​ | Serious​
Issues with processing units in Colab such as GPU ​ | Tools​ | Project ​ | Due to working with large data and large codes, GPU may be required to be able to process codes faster. ​ | Google Colab has limits on GPU and after running too many codes GPU it can ban you from using it for a while and force to change to CPU.​ | As a team we have agreed to invest into Google Colab Pro version which allows us to use GPU at all times with no limit. ​ | GPU changes to CPU, the time it takes to run the codes is significantly longer. ​ | High ​ | Catastrophic​
Industry and company changes ​ | ​ | Project ​ | Companies can change their regulations and access and things that were accessible before might no longer be. A good example of this is tweeter. ​ | Companies could limit access to their data or change regulations that allow access their tools and this can cause issues, especially if you were able to access it previously. ​ | Ensure to keep up to date with any major changes companies make regarding their tools, regulations and accessability. ​ | Unable to access tools that were previously accessible. ​ | High ​ | Serious-Catastrophic​
Member of team falling ill ​ | People​ | Project and product ​ | A member of the team will become sick during the project.​ | The required task is not finished by the deadline. Development time is put at risk.​ | Communication with team, making other members aware of sickness and scrum master taking over the tasks that require finishing ​ | A member of team missing lectures, signs of illness by a member of team. ​ | Moderate​ | Significant​
Wrong time estimation for a task​ | Estimation​ | Project and product​ | Wrong time have been estimated for a specific task​ | Required task takes longer than expected, requiring more time, could lead to having less time for other tasks.​ | Making sure estimations are created for a worst-case scenario, the longest time possible which reduces the risk of task going over the estimated time.​ | The task is reaching its dedicated hours and is nowhere near finished. Issues with complications of the task could add to the hours needed to complete it. ​ | Moderate-High​ | Serious-Catastrophic​
Lack of system knowledge ​ | Tools​ | Project​ | Team members may not be familiar with systems needed for the project ​ | Team members will need training on the system before beginning the work. This will lead to additional hours spent on training and less time to work on project. ​ | Make sure to discuss and agree on systems that most members are familiar with. Provide help and training for members who can’t use systems in their free time to reduce the time spent on training. ​ | Member of staff not being confident in using a system or avoiding using it. ​ | Moderate​ | Tolerable​
Wrong Requirement understanding ​ | Requirements​ | Project ​ | The team doesn’t understand familiarise themselves fully with all the requirements needed for the project ​ | There will be many changes to the requirements than anticipated​ | Make sure to read all the requirements before starting the work on the project. Make all the requirements clear and make sure the whole team understands all of them at the beginning of the project. ​ | Many requirement changes requests from scrum masters or customer. ​ | Moderate​ | Serious​