## Sheet1
Sprint No | Sprint Goal | Sprint Tasks | Start Date | End Date | Scrum Master | Daily Stand-up 1 | Daily Stand-up 2 | Daily Stand-up 3 | Sprint Review
1 | • Research about web scraping and sentiment analysis • Implementing web scraping and gather data • Data pre-processing and cleaning for maximum accuracy | Signing group contract Finalizing project topic Aims and objectives Making presentation skeleton Risk assessment table Making GitHub repository Provide a code for web scraping Clean the collected data | 2024-02-26 | 2024-03-18 | Diba | Date: 27/03 Meeting Time: 12:00 Discussion of: Project initiation Yesterday achievements, today’s plans and blockers: Talking about project initiations (discuss project topic, and assigning roles) | Date: 04/04 Meeting Time: 11:00 (online) Discussion of: Yesterday achievements, today’s plans and blockers: Checking the code for web-scraping, discuss branches of AI and divide them between ourselves for performing web-scraping Blocker: trying to provide a code for scraping Twitter but none of our codes are working and we need legal permission | Date: 13/03 Meeting Time: Discussion of: Yesterday achievements, today’s plans and blockers: Checking the data provided by all team members, combine them into a single file, perform data pre-processing and cleaning Blocker: didn’t know what to do with numbers in the sentences, labels from TextBlob library was not accurate | Date: 18/03 Meeting Time: Review, discover and rearrange information Do first steps of project management Research about ML models and libraries for sentiment analysis Provide the code for web-scraping and apply it to several websites Rewrite the code using a more accurate library for sentiment analysis Cleaning data
2 | • Researching how to scrape podcasts and deciding what kind of podcast to scrape • Working on coding file – also using DeepGram, to scrape data to collect data for AI in different sectors. (Data Understanding) • Data pre-processing, cleaning and then putting it into csv files for modelling (Data preparation) • Project Planning on MS Project • Updating Github with all files | Researching about scraping for speech-to-text Scraping and collecting data with the help of coding/Deepgram Creating functional and non-functional requirements table Creating diagrams related to scraping and sentiment analysis Shifting from Trello to MS Project for Project Planning Uploading Speech-to-Text Coding Files for all topics to Github | 2024-03-18 | 2024-04-26 | Aleeza | Date: 12/04 Meeting Time: 11 – 1:30 PM Discussing and sorting the project plan, adding tasks into sprints, making sure dates and timings are correct. Finalizing 1st sprint before moving onto the 2nd sprint . Blocker: • The duration for optimistic, most likely and pessimistic column was depending on each other, changing duration is one changed the durations in others. • Unorganized- looking Gant Chart with text that we weren’t able to remove at the top of bars. Solution: Creating a different project plan starting from scratch, adding columns as duration 1,2,3 and 4 and renaming them. | Date: 15/04 Meeting Time: 12 PM onwards Working on speech-to text code to scrape podcasts for sentiment analysis. Trying code with different types of audios. Blocker: • Code not working with recorded audios and on different devices due to Broken Pipe error (connection error) , not finding a way of how to get podcasts directly from websites. • Cutting podcasts in parts to extract relevant parts only using audacity was time consuming Solution: • Using DeepGram to scrape podcasts being downloaded directly from websites. • Scraping the entire podcast/audio file instead of scraping parts. | Date: 18/04 Meeting Time: 11- 5:30 PM Changing duration in project plan to whole numbers instead of it being in decimals as advised, scraping podcasts for all topics from websites with Speech- to-text code using DeepGram by creating personal API from the DeepGram website and by making changes to old code to update it for audio scraping. Uploading Speech-to-text files to Github Blocker: Not being able to change decimals to whole numbers using formula and other methods. | Date: 26/04 Meeting Time: 11:00 - 14:00 The dataset of speech-to-text is ready after scraping for audios from websites using deepgram, the dataset was cleaned using nltk to remove any punctuation and separate the paragraphs to sentences which can then be judged on the bases of polarity(using Vader) then the datset was combine so that it can be used for the models. We went through the project plan, GitHub to update anything that was missing before moving on to sprint 3 which is to work on the model. The group blog has also been updated with the last few updates of the sprint.
3 | To create the following models: • Random Forest • Logistic Regression • Naïve Bayes • Decision tree To test each individual model To evaluate the models and pick the most accurate one using accuracy score, and evaluation matric such as F1 score, precision and recall. To update the presentation slides To create a demo | To research the below : • Random Forest • Logistic Regression • Naïve Bayes • Decision tree And create models using the above. To test each model using test plan. To evaluate each model. To pick the most accurate model and perform a sentimental analysis for each of our categories of research. To complete a sprint review. | 2024-04-26 | 2024-04-29 | Justyna | Date: 26/04 Meeting Time: 14:00 – 20:00 PM Discussion of: Models needed for exploration and for finding the most accurate model. We have agreed to explore, Random Forest, Logistic Regression, Naïve Bayes and Decision Tree. We have begun our work on creating first models. Blocker: Our Training data not having equal amount of positive, negative and neutral sentiment and this was causing issues with the models – inaccurate predictions. Solution: We have manually changed the data and deleted rows of data to create an even amount of each sentiment in our training data which has improved the models. | Date: 30/04 Meeting Time: 11:00 – 19:00 PM Discussion of: Models needed for the project. Our team has done researches for all of the models needed and we have created the models by the end of the meeting. Making our codes work in PyCharm. Blocker: Codes not working due to lack of some knowledge related to using the models. Using PyCharm, issues with code not working and not reading a file Solution: Further research regarding the models and codes using websites, books and YouTube videos. We have managed to figure out the issue with the code not working (our data file had some blank lines which PyCharm wasn’t able to read therefore it was erroring), after removing the blanks the code has worked and now, we can run our models in PyCharm. | Date: 01/05 Meeting Time: 10:00 – 17:00 PM Discussion of: Choosing the most accurate model and creating a model to perform the final sentimental analysis on our topics. Blocker: Displaying the results. We have been stuck for a while deciding on what is the best way to display the results so that they are showing the results clearly. Solution: As a team we have decided to display our results using bar chart as we think they are easy to read. | Date: 02/05 Meeting Time: 10:00 – 11:00AM We have completed our models and the final model and reached our final goal which was to perform sentimental analysis on our topics. We have created all the needed graphs needed to show the process of making our codes. We have finalised all the codes in GitHub and created the README file. We have updated the group blogs with all the progress we have made. Finally, we have almost completed the whole presentation and created a demo to show how our codes and data works.
Scum closure | To test all coding files using testing plan Update presentation content and blogs. To finish the final sprint – scrum closure Practice the presentation delivery. | To ensure the testing has been preformed and all the coding files are satisfactory and meet the criteria. To complete the presentation slides and ensure all information required is provided. To ensure that the group blogs are completed. To practice the presentation ready for the presentation day. | 2024-04-30 | 2024-05-03 | Justyna | Date: 02/05 Meeting Time: 12:00 – 22:00 PM Discussion of: Finishing the project. Completion of the PowerPoint presentation, and final test plan to ensure all codes are working and all versions of codes are submitted to GitHub. Blocker: Time. We have only had two days for scum closure. Solution: Members of the team to stay behind as long as possible, to ensure the project is completed |  |  | We have completed our project. We are very proud of what we have done as we have reached our aims nd objectives. We have finished the presentaion. We have uplodaded al the documents to GitHub including all coding files, diagrams and all project managemnt files. We have finalised our group blogs. We will now submit all of our work.